Behavioral Support Rule (5123-2-06) Implementation Plan

|  | June 1, 2022 – September 30, 2022 | October 1, 2022 and Ongoing |
| --- | --- | --- |
| Training | DODD training - virtual, online, or in-person Other resources as shared by DODD | DODD training - virtual, online, or in-person Other resources as shared by DODD |
| Technical assistance | - DODD OSSAS Regional Coordination Managers - DODD OSSAS Regional Support Facilitators - DODD Policy & Strategic Direction Cross-system Regional Liaisons - DODD Policy & Strategic Direction RMN Business Lead | - DODD OSSAS Regional Coordination Managers - DODD OSSAS Regional Support Facilitators - DODD Policy & Strategic Direction Cross-system Regional Liaisons - DODD Policy & Strategic Direction RMN Business Lead |
| Citations | No citations unless action/activity is a violation of 5123-2-06 as it exists | Citations when there is substantial non- compliance with updated 5123-2-06 |
| Human Rights Committees | Examine practices to determine if changes to process are necessary Note changes to individual/guardian HRC notification and potential participation | Requirements of updated 5123-2-06 must be met |
| Policies and procedures | Examine and update policies and procedures | Policies and procedures should align with updated 5123-2-06 |
| Existing individual service plans that include restrictive measures | Boards/ICFs should develop a plan to identify and revise existing plans that are not in compliance with updated rule. All revisions and annual plans should be completed by June 30, 2023. | All new initial and emergency plans as of October 1, 2022 or after must be in compliance When plans previously containing restrictive measures come up for annual review, plans must be in compliance with updated 5123-2-06 after that review |
| Medications that chemically restrain a person | Encouraged to evaluate existing plans with chemical restraints to determine if any changes will need to be made. All changes should be completed by June 30, 2023. Identify those individuals without a chemical restraint in their plan who are experiencing a blunt suppression of behavior as a result of receiving medication intended for a physical or psychiatric condition. If any individuals are identified, initiate the process of seeking further consultation with the prescriber as well as team review. | All new initial and emergency plans as of October 1, 2022 or after must be in compliance When plans previously containing restrictive measures come up for annual review, plans must be in compliance with updated 5123-2-06 after that review |
| Restrictive Measure Notifications | Encouraged to begin submitting entries for discontinuations along with implementation start entries | All plans must be in compliance with updated 5123-2-06 |
| Annual analysis of data | Encouraged to examine annual analysis practices and update as necessary | Annual analysis practices should be updated and finalized in preparation for end-of-year submission to HRC by March 15th of the upcoming year for the current year |